## Sheet1
Risk Details |  | Risk Identification |  |  |  |  | Response Strategy |  |  |  |  | Reflection
Risk ID | Date Identified | Name Of Risk | Risk Description | Probability | Impact | Stage Of Project | Strategy To Mitigate | Risk Occured | When did it occur | Action Taken | Length Of Impact (HRS) | Future Risk
1 | 2021-01-02 | Lack of knowledge | Being new to the industry and learning from scratch | High | Medium | Continuous | Work hard and follow through on plans and practice | Yes | Points throughout the project that were unlcear to me | Read through QA Community, contacted Alan for guidence | 2 | This will always be risk - however reflection on what was learned can mitigate this secific risk happened again
2 | 2021-01-02 | Illness | Any kind of illness inc COVID-19 pandemic | Medium | High | Continuous | Reduce encounters - following the governments guidlines | No | Has not occured | No action needed | 0 | Hopefully there wont be one similar to this - but there is always the risk that another pandemic will happen
3 | 2021-01-02 | Laptop Issues | Any issues inc spilling something on laptop/breakages | Medium | High | Continuous | Make sure desk is clear and all work is backed up via GitHub | No | Has not occured | No action needed | 0 | There is always the possibility that something will break, you just make sure that everything you have is always backed up
4 | 2021-01-02 | Stress | Over working with no breaks | Medium | Medium | Continuous | Make sure to take regular breask to rest | No | Has not occured | No action needed | 0 | This will always be a risk because of the inrease in working from home due to the pandemic
5 | 2021-05-02 | Scope Creep | Always deleiver what the client has asked for | Low | High | Continuous | Make sure tsticking to the briefs | No | Has not occured | No action needed | 0 | Even when working in a team clarify the MVP and make sure you are onn the same page as the client
6 | 2021-06-02 | Merge Conflicts | Any conflicts that could dely rollout of the applicatin | Low | Medium | Continuous | feature branch model - branching off one at a time with versions | No | Has not occured | No action needed | 0 | Individually easy to accompish with no risk, but in a group commiunicaion is needed and plans in place so this doesnt happen
7 | 2021-06-02 | Internet Connection | Drop in internet connection | Medium | Medium | Continuous | Have a separte way to connect with trainer other than relying on wifi (Teams application on phone) | Yes | At points throughout the project | Needed to re-connect/wait for the router to reboot, messaged alan using teams on phont to make him aware of the loss of connection | 1 | During a call the internet might drop and i may be iconnected from the meeting without warning
8 | 2021-06-02 | Home Working | this relates more to desk set up - eye strain - comfort | High | Medium | Continuous | regular breaks - contrast on monitor ammended - chair set up correct - Followed HSE guidance | No | Has not occured | No action needed | 0 | Maybe projects where i need to adjust my setup in order to accomodate different working hours etc..
9 | 2021-06-02 | Tech Incompatibility | Software Downloads | Low | Medium | Begining/setup | always download a stable version of the software - and read up on compatibility with already installed software | No | Has not occured | No action needed | 0 | Compatibility may change with updates so always check regularly to make sure that everything sti works in tandem
10 | 2021-07-02 | Time Management | Make sure to plan to hit the target and goals set out | High | High | Continuous | planned from the beginning the order of priority tasks took and made sure to accomplish MVP before anythign else | No | Has not occured | No action needed | 0 | In the future teams need to be aware of the sprint times and make sure that if something is a must - it is completed without hesitations
11 | 2021-08-02 | Childcare | Working at home with child being with me | High | High | wc/8th | Make sure childcare is arranged and ability to schedule in project time to make sure that the project is compelted | Yes | W/C 8th - CRUD for JS begun | Continuous contact with childcare to make sure they are aware of the timings for the days | 2 | I may not be able to get childcare in the furture, this is something i will need to discuss with employer around what action can be taken
| Risks Occured | Impacted Time
| 3 | 5